## Checklist
Meeting Schedule Checklist & Calculator |  |  |  | Version 1.0 | 2013-11-08
Rapporteur meeting Date | Start date: | 2013-06-17 | End date: | 2013-06-21
Start of next SG/WP meeting | 2013-10-28
Role
Task | Deadline (before meeting) | Meeting Host | Meeting Organiser | Document Manager | Delegates
Provide logistic information | > 9 weeks | 2013-04-15
Invitation | > 8 weeks |  | 2013-04-22
Reminder | > 5 weeks |  | 2013-05-13
Authorisation | > 4 weeks |  | 2013-05-20
Confirmation | > 3 weeks |  | 2013-05-27
Agenda | >1 week |  | 2013-06-10
Meeting |  |  | 2013-06-17
Reporting | Before next SG/WP meeting |  | 2013-10-07
Create directory/templates | (before invitation) |  |  | 2013-04-22
Send updated doc. List to Meeting Organiser | 4 weeks |  |  | 2013-05-20
Document Reg reminder | Doc. Reg. - 1 week |  |  | 2013-05-27
Document Submission Reminder | Doc. Sub. - 1 week |  |  | 2013-05-31
Issue document list | 1 week |  |  | 2013-06-10
Publish document list |  |  |  | 2013-06-21
Send liaison statements | < 7 days |  |  | 2013-06-28
Document Registration Deadline | 14 days before |  |  |  | 2013-06-03
Document Submission Deadline | 10 days before |  |  |  | 2013-06-07